## Indicative Timeline
Website Timing Plan
| W/C 10th Nov |  |  |  |  | W/C 17th Nov |  |  |  |  | W/C 24th Nov |  |  |  |  | W/C 1st Dec |  |  |  |  | W/C 8th Dec |  |  |  |  | W/C 15th Dec
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Template Designs | bar: W/C 10th Nov M to W/C 10th Nov W
Template Design Feedback | bar: W/C 10th Nov W to W/C 10th Nov F
Website Development | bar: W/C 17th Nov M to W/C 1st Dec F
Content Migration | bar: W/C 1st Dec T to W/C 1st Dec F
Content Migration | bar: W/C 1st Dec T to W/C 1st Dec F
Website Design Feedback | bar: W/C 8th Dec M to W/C 8th Dec F
Website Design Amends | bar: W/C 15th Dec M to W/C 15th Dec F
Weekly Check-in | bar: W/C 10th Nov T; W/C 17th Nov T; W/C 24th Nov T; W/C 1st Dec T; W/C 8th Dec T; W/C 15th Dec T
AHK
EBY
Both

## Site Diagram (hidden)
Item | Owner | Comments | Complete | Site | Tier 1 | Tier 2 | Tier 3 | Tier 4
%age
1 | SW |  |  | AmuletHotkey.com HOME PAGE
2 |  | Menu Item |  |  | Solutions
3 | JG | Review / Update Copy & Content |  |  |  | Financial Services
4 | PvO | Review / Update Copy & Content |  |  |  | Government & Defence
5 | TH | Needs Content & Copy - TH decide post Golive or not |  |  |  | Media & Entertainment
6 | TH | Needs Content & Copy - TH decide post Golive or not |  |  |  | Industrial Automation
8 | TC | Remove / Hide Page - Make Menu Item? |  |  | Products
9 | JG | Needs complete Review, Copy & Content |  |  |  | Remote Workstations
10 |  | No Action Required |  |  |  |  | CoreStation.com
11 |  | No Action Required | [5 empty] | CoreStation HX2000
12 |  | No Action Required | [5 empty] | CoreStation HX3000
13 |  | No Action Required | [5 empty] | CoreStation RX360
14 |  | No Action Required | [5 empty] | CoreStation RX660
15 |  | No Action Required
16 |  | No Action Required |  |  |  |  | FAQs
17 |  | No Action Required |  |  |  |  | CoreStation HX
18 |  | No Action Required |  |  |  |  | CoreStation RX
19 |  | No Action Required |  |  |  |  | CoreStation CX
20 |  | No Action Required |  |  |  |  | CoreStation Test Drive | Terms & Conditions
21 | TC & JG | Create Copy & Content |  |  |  |  | HP Anyware Professional
22 | TC & JG | Create Copy & Content |  |  |  |  | Citrix Remote PC Access
23 | TC & JG | Create Copy & Content |  |  |  |  | Leostream Platform
24 | TC | Review / Update Copy & Content |  |  |  | Thin & Zero Clients
25 | TC | New Page - Copy & Content |  |  |  |  | Secure Thin Clients
26 | TC | Review / Update Copy & Content | [5 empty] | DX1500s & DX1700s
27 | TC | New Page - Copy & Content | [5 empty] | DX2500s
28 | TC | New Page - Copy & Content |  |  |  |  | Trusted Zero Clients
29 | TC | Review / Update Copy & Content | [5 empty] | DXZ130
30 | TC | Review / Update Copy & Content | [5 empty] | DXZ160-R
31 | TC | New Page - Copy & Content |  |  |  |  | MagNOS Zero Client
32 | TC | New Page - Copy & Content | [5 empty] | MagNOS Client
35 |  | Menu Item |  |  | About Us
36 | TH & SW | Review / Update Copy & Content |  |  |  | Why Amulet Hotkey
37 | TH & SW | Review / Update Copy & Content |  |  |  | Meet The Team
38 |  | No Action Required |  |  |  | News
39 | TH & SW | Review / Update Copy & Content |  |  |  | Our Customers
40 | TH & SW | Review / Update Copy & Content |  |  |  | Technology Partners
41 | TH & SW | Review / Update Copy & Content |  |  |  | Careers
42 |  | Menu Item |  |  | How To Buy
43 | TH | Review How to Buy Structure |  |  |  | Request A Quote
44 | TH | Review How to Buy Structure |  |  |  | Authourised Resellers
45 |  | Menu Item (Contact Us?) |  |  | Help & Support
46 | TH & SW | New Page - Create Copy & Content |  |  |  | General FAQs
47 |  | No Action Required |  |  |  | Technical Support
48 |  | No Action Required |  |  |  | Drivers & Downloads
49 |  | Review Contact Us along with How to Buy |  |  |  | Contact Us
50 | CD | Review / Update Copy & Content |  |  |  |  | Warranty Page
51 | [6 empty] | Privacy Policy

## Updated Diagram
Item | Owner | Comments | Complete | Site | Tier 1 | Tier 2 | Tier 3 | Tier 4
%age
1 | SW |  |  | AmuletHotkey.com HOME PAGE
2 |  | Menu Item |  |  | Solutions
3 | JG | Review / Update Copy & Content | Wk49 |  |  | Financial Services
4 | PvO | Review / Update Copy & Content | TGH to discuss with PVO |  |  | Government & Defence
5 | TH | Needs Content & Copy - TH decide post Golive or not |  |  |  | Media & Entertainment
6 | TH | Needs Content & Copy - TH decide post Golive or not |  |  |  | Industrial Automation
7 | TC | Menu Item |  |  | Products
8 | JG | Needs complete Review, Copy & Content | Wk49 |  |  | Remote Workstations
9 |  | No Action Required |  |  |  |  | CoreStation.com
10 |  | No Action Required | [5 empty] | CoreStation HX2000
11 |  | No Action Required | [5 empty] | CoreStation HX3000
12 |  | No Action Required | [5 empty] | CoreStation RX360
13 |  | No Action Required | [5 empty] | CoreStation RX660
14 |  | No Action Required |  |  |  |  | FAQs
15 |  | No Action Required |  |  |  |  | CoreStation HX
16 |  | No Action Required |  |  |  |  | CoreStation RX
17 |  | No Action Required |  |  |  |  | CoreStation CX
18 |  | No Action Required before Go-Live |  |  |  |  | CoreStation Test Drive | Terms & Conditions
19 | TC & JG | Create Copy & Content - use existing slides, post go-live |  |  |  |  | HP Anyware Professional
20 | TC & JG | Create Copy & Content - use existing slides |  |  |  |  | Citrix Remote PC Access
21 | TC & JG | Create Copy & Content - use existing slides |  |  |  |  | Leostream Platform
22 | TC | Review / Update Copy & Content - INCLUDES FAQs |  |  |  | Thin & Zero Clients
23 | TC | New Page - Copy & Content |  |  |  |  | Secure Thin Clients
24 | TC | Review / Update Copy & Content | [5 empty] | DX1500s & DX1700s
25 | TC | New Page - Copy & Content | [5 empty] | DX2500s
26 | TC | New Page - Copy & Content |  |  |  |  | Trusted Zero Clients
27 | TC | Review / Update Copy & Content | [5 empty] | DXZ130
28 | TC | Review / Update Copy & Content | [5 empty] | DXZ160-R
29 | TC | New Page - Copy & Content - | Discuss with PvO |  |  |  | MagNOS Zero Client
30 | TC | New Page - Copy & Content | [5 empty] | MagNOS Client
31 |  | Menu Item |  |  | About Us
32 | SW | Review / Update Copy & Content | SW to kick off |  |  | Why Amulet Hotkey
33 | SW | Review / Update Copy & Content | SW to kick off |  |  | Meet The Team
34 |  | No Action Required |  |  |  | News
35 | TH | Review / Update Copy & Content |  |  |  | Our Customers
36 | TH | Review / Update Copy & Content |  |  |  | Technology Partners
37 | SW | Review / Update Copy & Content | SW to kick off |  |  | Careers
38 |  | Menu Item |  |  | How To Buy
39 | SW | Remove Authorised Resellers link |  |  |  | Request A Quote
40 | Sales SW | Review list of resellers SW review page layout |  |  |  | Authorised Resellers
41 |  | Menu Item (Contact Us?) |  |  | Help & Support
42 | SW | Delete |  |  |  | Request A Quote
43 | SW + Sales | New Page - Create Copy & Content |  |  |  | General FAQs
44 |  | Minor Update Page Copy (text) |  |  |  | Technical Support
45 | CD | Remove Documentation & Update Page Copy (text) | Not critical for phase 1 |  |  |  | Raise a Ticket
46 | CD | Rename Drivers & Documentation | Not critical for phase 1 |  |  | Drivers & Documentation
47 | CD | Rename Contact Us to ProCare & update Copy | Not critical for phase 1 |  |  | ProCare
48 | SW | Add to ProCare page | Not critical for phase 1 |  |  |  | Warranty Page
49 | EBY/SW | Review / Update Copy & Content | Not critical for phase 1 |  |  |  | Privacy Policy

## Site Map
Item | Owner | Comments | Tier 1 | Tier 2 | Tier 3
1 |  |  | Home Page
2 |  |  | Solutions
3 | JG |  |  | Financial Services
4 | PvO |  |  | Government & Defence
5 | TH | Discuss separately, Post Go-live? TH to decide |  | Media & Entertainment
6 | TH | Discuss separately, Post Go-live? TH to decide |  | Industrial Automation
7 |  |  | Products
8 |  |  |  | CoreStation (change to Remote Workstation) | Briefly introduce these products and link to the relevant pages on corestation.com
9 |  |  |  | FAQs | CoreStation HX | LINK TO CS.COM
10 |  |  |  |  | CoreStation RX
11 |  |  |  |  | CoreStation CX
12 |  |  |  |  | CoreStation Test Drive
13 | [5 empty] | Test Drive Terms & Conditions
14 | TC |  |  | Thin and Zero Clients (update page with new design)
15 | TC |  |  | Secure Thin Clients
16 | TC |  |  | FAQs | DX1500
17 | TC |  |  |  | DX1700 update and combine with DX1500
18 | TC |  |  | Trusted Zero Clients | Trusted Zero Clients
19 | TC |  |  |  | DX1300
20 | TC |  |  |  | DX1600-R
21 |  | Hidden, linked from CS pages |  | Remote Workstation (update page with new design) Intro the solution and link to the relevant solution brief |  | Hide pages from main navigation
22 |  |  |  |  | Anyware Professional
23 | TC/JG | Someone to resolve page structure /location |  |  | Citrix Remote PC Access
24 |  |  |  |  | Leostream Platform
25 | TC | Decide structure |  | Legacy Products
26
27
28
29 |  |  | About Us
30 | SW/TH |  |  | Why Amulet Hotkey
31 |  |  |  | Meet The Team
32 |  |  |  | News
33 |  |  |  | Our Customers
34 |  |  |  | Technology Partners
35 |  |  |  | Careers
36
37 |  |  | How To Buy
38 |  |  |  | Request A Quote
39 |  |  |  | Authorised Resellers
40 |  |  | Help & Support
41 |  |  |  | Technical Support
42 |  |  |  | Drivers & Downloads
43 | SW/TH | General FAQs |  | FAQ's
44 |  |  |  | Contact Us
45 |  |  |  |  | Warranty Page
46 |  |  |  |  | Privacy Policy